## Sheet1
Gantt Chart For Project Scince For Genius
|  | Start Date : |  |  |  | 2026/08/26
|  | End Date : |  |  |  | 2026-11-24
Task Name |  | Aug 26 | [6 empty] | Sep 06 | [6 empty] | Sep 13 | [6 empty] | Sep 20 | [6 empty] | Sep 27 | [6 empty] | Oct 04 | [6 empty] | Oct 11 | [6 empty] | Oct 18 | [6 empty] | Oct 25 | [6 empty] | Nov 01 | [6 empty] | Nov 08 | [6 empty] | Nov 15 | [6 empty] | Nov 22 | [6 empty] | Nov 29
|  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
1 | Requiments Gathring | bar: Aug 26 W
2 | Project Architec | bar: Aug 26 W
3 | Project Development
4 | Database ER Development | bar: Aug 26 W
5 | Project Struscture Development | bar: Aug 26 W
6 | UI/UX Desing
7 | Student Portal
8 | Student Login / Register | bar: Aug 26 W to Sep 06 S
9 | Student Dashboard | bar: Sep 06 T to Sep 13 S
10 | Admin Portal
11 | Admin Login | bar: Aug 26 W to Sep 06 S
12 | Admin Dashboard | bar: Sep 20 M to Sep 27 S
13 | Backend Development | bar: Oct 04 S to Oct 18 W
14 | Telegram Bot Intergration | bar: Oct 18 T to Oct 25 T
15 | Project Tesing | bar: Oct 25 T to Nov 08 W
16 | Finalize Project | bar: Nov 08 T to Nov 15 M
17 | Project Deploy | bar: Nov 15 T to Nov 15 S
18 | Project Handover | bar: Nov 22 S to Nov 22 T